MINUTES No. 14

of the working meeting on the CRM system implementation

| Date and time: | 10 July 2026, 10:00–11:30 |
| --- | --- |
| Location: | London, Vector Dynamics Ltd. office, meeting room 3 / video conference |
| Subject: | CRM implementation progress and preparation for go-live in the sales team |
| Chair: | J. Whitfield |
| Secretary: | O. Bennett |

ATTENDEES

| No. | Name | Position | Format |
| --- | --- | --- | --- |
| 1 | James Whitfield | Commercial Director | in person |
| 2 | Olivia Bennett | Head of Project Office | in person |
| 3 | Thomas Grant | Head of Sales | in person |
| 4 | Anna Sinclair | IT Director | in person |
| 5 | Ian Prescott | Lead IT Analyst | video call |
| 6 | Kate Sherwood | Head of Learning and Development | video call |

A quorum for taking decisions is present. No one on the agenda was absent.

MEETING AGENDA

- CRM implementation status: results of the configuration and integration stage.

- Migration of the customer database from the legacy spreadsheets: data quality and migration timeline.

- Training the sales team to work in the CRM.

- Go-live date for production use and the transition period.

DISCUSSION AND DECISIONS

Item 1. CRM implementation status

PRESENTED: Anna Sinclair — on completion of the CRM base configuration stage: sales pipelines, customer records and access rights are configured; integration with telephony and corporate email is done. Integration with the ERP system is delayed by 5 working days because the product catalogue exchange needs rework.

DISCUSSED: Ian Prescott — proposed not to block the overall go-live because of the ERP integration and to ship the data exchange in a second release. James Whitfield — supported this, provided that a manual invoice export is available before go-live.

RESOLVED: 1.1. Accept the configuration and integration stage as 90% complete. 1.2. Move the ERP integration to the second release, ready by 24 July 2026. 1.3. Until the second release, put a temporary manual invoice export procedure in place (owner — Ian Prescott).

Item 2. Customer database migration

PRESENTED: Ian Prescott — on the results of the trial migration: 12,400 records were transferred, about 8% duplicates and 3% records without contact details were found. A full migration is feasible within 3 working days once the data is cleaned.

DISCUSSED: Thomas Grant — noted that duplicate clean-up must be validated by the account managers who own the respective customers, otherwise deal history may be lost. Olivia Bennett — proposed assigning each manager their own segment of the database and setting a one-week validation deadline.

RESOLVED: 2.1. Approve the clean-up procedure: automatic deduplication by IT, followed by validation by the managers on their assigned segments. 2.2. Complete validation by 17 July 2026 and the full migration by 22 July 2026.

Item 3. Sales team training

PRESENTED: Kate Sherwood — on the training programme: two 3-hour in-person workshops, a video course of 8 modules and a knowledge base with instructions. Materials are 80% ready.

DISCUSSED: Thomas Grant — asked to include a walkthrough of the team's real deals in the programme, not only generic scenarios. James Whitfield — proposed a mandatory final test with an 80% pass mark.

RESOLVED: 3.1. Extend the training programme with a workshop based on the sales team's real deals. 3.2. Introduce a final test (pass mark — 80% correct answers); access to the CRM only after passing it. 3.3. Run the training between 20 and 24 July 2026.

Item 4. Go-live date and transition period

PRESENTED: James Whitfield — on the target date for moving the system into production use and the risks of keeping records in the old spreadsheets in parallel.

DISCUSSED: Olivia Bennett — proposed a two-week transition period during which the old spreadsheets are available read-only. Anna Sinclair — confirmed technical readiness to switch the spreadsheets to read-only from the go-live date.

RESOLVED: 4.1. Set the CRM production go-live date to 27 July 2026. 4.2. From 27 July 2026 switch the legacy spreadsheets to read-only; the transition period runs until 7 August 2026. 4.3. Review the go-live results at the next meeting on 10 August 2026.

ACTION ITEMS FROM THE MEETING

| No. | Action item | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| 1 | Prepare and approve a temporary manual invoice export procedure until the ERP exchange goes live | I. Prescott | 16 Jul 2026 | in progress |
| 2 | Assign customer database segments to the managers and organise validation after deduplication | T. Grant | 17 Jul 2026 | in progress |
| 3 | Run the full customer database migration into the CRM once validation is complete | I. Prescott | 22 Jul 2026 | in progress |
| 4 | Extend the training programme: workshop on real deals and a final test (80% pass mark) | K. Sherwood | 18 Jul 2026 | in progress |
| 5 | Deliver the sales team training and report on the test results | K. Sherwood | 24 Jul 2026 | in progress |
| 6 | Finish the rework and ship the CRM–ERP integration (second release) | A. Sinclair | 24 Jul 2026 | in progress |
| 7 | Switch the legacy spreadsheets to read-only from the go-live date | A. Sinclair | 27 Jul 2026 | in progress |
| 8 | Prepare a consolidated action-item status report for the next meeting | O. Bennett | 10 Aug 2026 | in progress |

Responsibility for tracking the action items is assigned to Olivia Bennett, Head of the Project Office. These minutes are to be circulated to all attendees within one working day.

| Meeting chair |  | Meeting secretary |
| --- | --- | --- |
| _______________ / J. Whitfield / |  | _______________ / O. Bennett / |